## Master Stories
ID | Epic | Priority | Estimate | Owner | Sprint | Status | Story | Acceptance Criteria | Dependencies | Notes
CFM-001 | Project Foundation | P0 | 2 |  |  | Backlog | Scaffold standalone VS Code extension package under `codefresh-actions-migrator`. | Package has compile/test scripts, TypeScript config, VS Code extension manifest, and local README.
CFM-002 | Project Foundation | P0 | 2 |  |  | Backlog | Configure extension activation, commands, and contributed chat participant metadata. | Extension activates on migration commands and `@cfmigrator`; command palette entries are visible. | CFM-001
CFM-003 | Project Foundation | P1 | 3 |  |  | Backlog | Define public migration domain interfaces. | `CodefreshPipeline`, `CodefreshStep`, `MigrationPlan`, `StepMapping`, and `KnowledgePattern` are exported and covered by compile-time checks. | CFM-001
CFM-004 | Project Foundation | P1 | 3 |  |  | Backlog | Establish repository hygiene for generated artifacts. | `node_modules`, `out`, `.vscode-test`, and packaged VSIX files are ignored. | CFM-001
CFM-005 | Project Foundation | P2 | 3 |  |  | Backlog | Add contribution/development guide for local extension development. | README explains install, compile, test, debug launch, and manual smoke-test workflow. | CFM-001
CFM-006 | Deterministic Converter Core | P0 | 3 |  |  | Backlog | Scan workspaces for Codefresh pipeline files. | Scanner finds `codefresh.yml`, `codefresh.yaml`, and `.codefresh/*.yml` while skipping noisy folders. | CFM-003
CFM-007 | Deterministic Converter Core | P0 | 5 |  |  | Backlog | Parse Codefresh YAML into a normalized pipeline model. | Parser validates YAML, extracts version, variables, and ordered steps, and reports parse errors clearly. | CFM-003
CFM-008 | Deterministic Converter Core | P0 | 3 |  |  | Backlog | Normalize freestyle, build, push, composition, approval, deploy, and unknown steps. | Analyzer consistently extracts type, title, image, commands, env, `when`, and raw fields. | CFM-007
CFM-009 | Deterministic Converter Core | P0 | 5 |  |  | Backlog | Map Codefresh git clone and freestyle steps to GitHub Actions. | Clone becomes `actions/checkout@v4`; freestyle becomes `run`; container/image behavior is warned or mapped. | CFM-008
CFM-010 | Deterministic Converter Core | P1 | 5 |  |  | Backlog | Map Docker build and push patterns. | Build uses Buildx/build-push-action; push includes registry login, required secrets, and verification warnings. | CFM-008
CFM-011 | Deterministic Converter Core | P1 | 5 |  |  | Backlog | Map composition and service patterns. | Representable services become job services; unsupported compose behavior becomes a guarded `docker compose` step with warnings. | CFM-008
CFM-012 | Deterministic Converter Core | P1 | 5 |  |  | Backlog | Map approval and deploy patterns safely. | Approval maps to GitHub environment with reviewer warning; deploy commands are preserved or flagged for manual migration. | CFM-008
CFM-013 | Deterministic Converter Core | P1 | 4 |  |  | Backlog | Handle unknown/custom steps without hallucinated production workflow code. | Unknown steps become explicit manual-review placeholders and low-confidence mappings. | CFM-008
CFM-014 | GitHub Actions Generation | P0 | 5 |  |  | Backlog | Build migration planner that aggregates mappings, warnings, secrets, and confidence. | Planner emits one deterministic `MigrationPlan` with target workflow path and job plan. | CFM-009, CFM-010, CFM-011, CFM-012, CFM-013
CFM-015 | GitHub Actions Generation | P0 | 5 |  |  | Backlog | Generate GitHub Actions workflow YAML. | Generator emits `name`, `on`, `jobs`, `runs-on`, steps, container, services, and environment as valid YAML. | CFM-014
CFM-016 | GitHub Actions Generation | P0 | 3 |  |  | Backlog | Validate generated workflow shape before writing. | Validator rejects malformed YAML and missing `name`, `on`, or `jobs`. | CFM-015
CFM-017 | GitHub Actions Generation | P1 | 5 |  |  | Backlog | Add branch/trigger strategy configuration. | User can choose default triggers or supply workspace setting defaults without code changes. | CFM-015
CFM-018 | GitHub Actions Generation | P2 | 5 |  |  | Backlog | Improve GitHub Actions fidelity for Codefresh `when` conditions and parallel execution. | Common conditions and parallel step groups map to equivalent Actions expressions/jobs or produce clear warnings. | CFM-014
CFM-019 | VS Code Extension UX | P0 | 3 |  |  | Backlog | Implement `scanWorkspace` command. | Command scans open workspace, shows result count, and logs files to output channel. | CFM-006
CFM-020 | VS Code Extension UX | P0 | 5 |  |  | Backlog | Implement `planMigration` command. | User can pick a pipeline and view a Markdown migration plan preview. | CFM-014, CFM-019
CFM-021 | VS Code Extension UX | P0 | 5 |  |  | Backlog | Implement `generateWorkflow` command with preview and confirmation. | Extension previews YAML, validates it, writes only after confirmation, and asks before overwrite. | CFM-015, CFM-016, CFM-020
CFM-022 | VS Code Extension UX | P1 | 5 |  |  | Backlog | Implement `explainMigration` command. | Command opens a concise migration explanation using Copilot when available and deterministic fallback otherwise. | CFM-020, CFM-027
CFM-023 | VS Code Extension UX | P1 | 5 |  |  | Backlog | Improve migration plan preview UX. | Preview includes grouped warnings, required secrets, confidence, and step mapping table. | CFM-020
CFM-024 | VS Code Extension UX | P2 | 6 |  |  | Backlog | Add tree view for pipeline inventory and migration status. | Activity view lists discovered pipelines, planned/generated state, warnings, and target workflow path. | CFM-019, CFM-020, CFM-021
CFM-025 | Copilot and AI Tooling | P0 | 5 |  |  | Backlog | Register `@cfmigrator` chat participant with slash commands. | `/scan`, `/plan`, `/generate`, and `/explain` return useful results in VS Code Chat. | CFM-019, CFM-020, CFM-021
CFM-026 | Copilot and AI Tooling | P0 | 5 |  |  | Backlog | Register language model tools for scan, plan, and validate. | Copilot agent mode can invoke `scan_codefresh_pipelines`, `plan_codefresh_migration`, and `validate_github_workflow`. | CFM-006, CFM-014, CFM-016
CFM-027 | Copilot and AI Tooling | P1 | 5 |  |  | Backlog | Add Copilot-backed explanation flow with graceful fallback. | Uses Copilot model when available; handles missing model, consent denial, quota, and empty responses. | CFM-014
CFM-028 | Copilot and AI Tooling | P1 | 5 |  |  | Backlog | Add strict JSON AI review contract for unknown-step suggestions. | AI suggestions validate against schema and are discarded if malformed or unsafe. | CFM-013, CFM-027
CFM-029 | Copilot and AI Tooling | P2 | 4 |  |  | Backlog | Add prompt templates for ambiguity resolution. | Chat participant can ask focused follow-up questions for unsupported deploy/composition/custom patterns. | CFM-025, CFM-028
CFM-030 | Knowledge and Learning | P1 | 3 |  |  | Backlog | Ship default mapping pattern library. | Repo includes `default-patterns.json` with clone, Docker, and approval patterns. | CFM-003
CFM-031 | Knowledge and Learning | P1 | 5 |  |  | Backlog | Initialize user override storage in VS Code global storage. | Extension creates a user pattern file if absent and never overwrites existing user patterns. | CFM-030
CFM-032 | Knowledge and Learning | P2 | 5 |  |  | Backlog | Add "learn this mapping" workflow. | User can save reviewed manual mappings into global storage and future plans consult those patterns. | CFM-028, CFM-031
CFM-033 | Testing and Quality | P0 | 5 |  |  | Backlog | Add unit fixtures for required Codefresh scenarios. | Fixtures cover freestyle Node, Docker build/push, composition, approval, deploy, and unknown/custom steps. | CFM-007
CFM-034 | Testing and Quality | P0 | 5 |  |  | Backlog | Add mapper/generator unit tests. | Tests verify generated YAML and warnings for all required fixtures. | CFM-009, CFM-010, CFM-011, CFM-012, CFM-013, CFM-015
CFM-035 | Testing and Quality | P0 | 3 |  |  | Backlog | Add validator tests. | Tests prove valid workflows pass and missing required top-level fields fail. | CFM-016
CFM-036 | Testing and Quality | P1 | 3 |  |  | Backlog | Add mocked Copilot tests. | AI flows are tested with mocked model responses and no real Copilot calls. | CFM-027, CFM-028
CFM-037 | Testing and Quality | P1 | 4 |  |  | Backlog | Add VS Code extension-host integration smoke test. | Extension activates and registers expected commands in `@vscode/test-electron`. | CFM-002, CFM-019
CFM-038 | Testing and Quality | P2 | 3 |  |  | Backlog | Add CI workflow for compile and tests. | Pull requests run install, compile, unit tests, and optional integration smoke test. | CFM-034, CFM-037
CFM-039 | Packaging and Documentation | P1 | 3 |  |  | Backlog | Document supported Codefresh mappings and known limitations. | Docs list supported step types, fallback behavior, required secrets, and manual review cases. | CFM-014
CFM-040 | Packaging and Documentation | P1 | 3 |  |  | Backlog | Add manual QA checklist for extension usage. | Checklist covers scan, plan, generate, overwrite protection, chat participant, and tools. | CFM-021, CFM-025, CFM-026
CFM-041 | Packaging and Documentation | P2 | 3 |  |  | Backlog | Add packaging script and VSIX verification. | `vsce package` or equivalent process is documented and package excludes dev artifacts. | CFM-001, CFM-004
CFM-042 | Packaging and Documentation | P2 | 4 |  |  | Backlog | Add sample migration walkthrough. | A sample Codefresh YAML and generated GitHub workflow are documented end to end. | CFM-039

## Summary
Codefresh to GitHub Actions Migrator - Backlog Summary
Metric | Formula / Value
Total stories
Total points
Unassigned stories
Blocked stories
Done stories
Epic | Story Count | Points
Project Foundation
Deterministic Converter Core
GitHub Actions Generation
VS Code Extension UX
Copilot and AI Tooling
Knowledge and Learning
Testing and Quality
Packaging and Documentation
Priority | Story Count | Points
P0
P1
P2
P3
Status | Story Count | Points
Backlog
Ready
In Progress
Blocked
Review
Done

## Field Guide
Field | Usage
ID | Stable story identifier for assignment and dependency tracking.
Epic | Functional workstream. Filter by this to distribute across teams.
Priority | P0 release blocker, P1 MVP, P2 important follow-up, P3 polish.
Estimate | Relative story points, not hours.
Owner | Person or team accountable for delivery.
Sprint | Target sprint or milestone.
Status | Use the dropdown: Backlog, Ready, In Progress, Blocked, Review, Done.
Dependencies | Comma-separated story IDs that should land first.
Notes | Assignment notes, links, or implementation comments.